## 00_Home
PROJECT ORION
Enterprise Change Management Suite
Document | PO-CHANGE-REGISTER_v1.0
Version | 1.0
Status | Draft
Sprint | 7.2
Owner | Project Orion
Purpose
This workbook supports enterprise change management, validation, governance, and audit readiness.
Workbook Navigation
01_Change_Register
02_Change_History
03_CAB_Meetings
04_Implementation_Checklist
05_Reference_Data
06_Revision_History
07_Dashboard

## 01_Change_Register
PROJECT ORION — ENTERPRISE CHANGE REGISTER
Governed tracking of infrastructure, security, application, and operational changes
Change ID | Change Title | Change Category | Change Type | Status | Risk Level | Priority | Linked CI ID | Asset ID | Requested By | Assigned Engineer | CAB Approval | Planned Start | Planned End | Actual Start | Actual End | Rollback Plan | Validation Status | Comments
CHG-000001 | Upgrade Core Firewall Firmware | Network | Standard | Planned | Medium | Medium | CI-NET-001 | AST-NET-001 | Infrastructure Team | Network Engineer | Yes | 2026-09-21 20:00 | 2026-09-21 22:00 |  |  | Yes | Pending | Scheduled maintenance window.
CHG-000002 | Patch Windows Domain Controller | Server | Normal | Approved | High | High | CI-SRV-001 | AST-SRV-001 | Security Team | Systems Engineer | Yes | 2026-09-22 19:00 | 2026-09-22 21:00 |  |  | Yes | Pending | Security patch deployment.
CHG-000003 | Rotate Cloud Service Credentials | Cloud | Normal | Completed | Medium | Medium | CI-CLD-001 | AST-CLD-001 | Cloud Operations | Cloud Engineer | Yes | 2026-09-15 18:00 | 2026-09-15 19:00 | 2026-09-15 18:05 | 2026-09-15 18:48 | Yes | Passed | Change completed and validated.

## 05_Reference_Data
Change Type | Status | Priority | Risk Level | CAB Approval | Validation Status | Change Category | Rollback Plan
Standard | Planned | Low | Low | Yes | Pending | Network | Yes
Normal | Approved | Medium | Medium | No | Passed | Server | No
Emergency | In Progress | High | High | N/A | Warning | Security
| Completed | Critical | Critical |  | Failed | Application
| Cancelled |  |  |  |  | Database
Cloud
Endpoint
Infrastructure