## 00_Home
Project Orion - Change Register
Workbook | PO-Change-Register_v1.0.xlsx
Document ID | EM-006
Version | 1.0
Sprint | 4
Engineering Session | 017
Status | Baselined
Purpose | Track and govern infrastructure changes across Project Orion.

## 01_Change_Register
Change Register
Change ID | Title | Linked CI ID | Asset ID | Related Maintenance ID | Change Type | Priority | Risk | Requested By | Scheduled Date | Implementation Date | Status | Rollback Plan | Evidence | Notes
CHG-001 | Upgrade Flint 2 Firmware | CI-003 | AST-003 | MNT-001 | Firmware | High | Medium | George Jordan | 2026-10-30 |  | Planned | Restore previous firmware | FW log
CHG-002 | Patch Windows 11 Host | CI-004 | AST-004 | MNT-002 | OS Patch | High | Medium | George Jordan | 2026-08-15 |  | Planned | System restore point | Patch report
CHG-003 | Upgrade Home Assistant | CI-006 |  | MNT-003 | Application | High | Low | George Jordan | 2026-08-20 |  | Planned | HA backup snapshot | Update log
CHG-004 | Deploy Doorbell | CI-007 | AST-006 | MNT-004 | Installation | Medium | Low | George Jordan | 2026-08-10 |  | Planned | Remove device | Photos

## 02_Approvals
Approvals
Change ID | Approver | Approval Date | Decision | Comments

## 03_Implementation_Log
Implementation Log
Change ID | Step | Engineer | Timestamp | Result | Evidence

## 04_Post_Implementation_Review
Post Implementation Review
Change ID | Review Date | Successful | Issues | Lessons Learned | Follow-up

## 05_Reference_Data
Reference Data
Status
Draft
Submitted
Approved
Planned
In Progress
Implemented
Closed
Rejected

## 06_Revision_History
Revision History
Version | Date | Author | Summary
1.0 | 2026-07-30 | George Jordan | Initial baseline

## 07_Dashboard
Dashboard
Metric | Value | Priority | Count
Total Changes |  | High
Planned |  | Medium
Implemented |  | Low
Closed