## 00_Home
Project Orion - Risk Register
Workbook | PO-Risk-Register_v1.0.xlsx
Document ID | EM-007
Version | 1.0
Sprint | 4
Engineering Session | 018
Status | Baselined
Purpose | Track operational, infrastructure, and cybersecurity risks across Project Orion.

## 01_Risk_Register
Risk Register
Risk ID | Title | Linked CI ID | Asset ID | Related Change ID | Category | Likelihood | Impact | Inherent Risk | Residual Risk | Owner | Treatment Strategy | Status | Review Date | Evidence | Notes
RSK-001 | Router firmware vulnerability | CI-003 | AST-003 | CHG-001 | Cybersecurity | Medium | High | High | Medium | George Jordan | Mitigate | Open | 2026-10-30 | Firmware review
RSK-002 | Server patch backlog | CI-004 | AST-004 | CHG-002 | Operations | Medium | High | High | Low | George Jordan | Mitigate | Open | 2026-08-31 | Patch records
RSK-003 | Home Assistant backup failure | CI-006 |  |  | Business Continuity | Low | High | Medium | Low | George Jordan | Mitigate | Monitoring | 2026-08-31 | Backup tests
RSK-004 | Camera outage | CI-008 | AST-007 |  | Availability | Low | Medium | Low | Low | George Jordan | Accept | Monitoring | 2026-09-30 | Health checks
RSK-005 | Unauthorized IoT access | CI-009 | AST-008 |  | Cybersecurity | Medium | High | High | Medium | George Jordan | Mitigate | Open | 2026-09-30 | Network segmentation

## 02_Risk_Treatments
Risk Treatments
Risk ID | Action | Owner | Target Date | Status | Notes

## 03_Risk_Reviews
Risk Reviews
Risk ID | Review Date | Reviewer | Residual Risk | Decision | Comments

## 04_Risk_Metrics
Risk Metrics
Metric | Value
Open Risks
Monitoring

## 05_Reference_Data
Reference Data
Treatment | Risk Level
Mitigate | Low
Accept | Medium
Transfer | High
Avoid | Critical

## 06_Revision_History
Revision History
Version | Date | Author | Summary
1.0 | 2026-07-30 | George Jordan | Initial baseline

## 07_Dashboard
Dashboard
Metric | Value | Inherent Risk | Count
Total Risks |  | High
Open |  | Medium
Monitoring |  | Low